## Slide 1
PHOENIX SOLUTIONS · EXECUTIVE STRATEGY
30 - 60 - 90 Day Business Growth Plan
Streamlined Phase-by-Phase Execution Blueprint for Market Expansion
EXECUTIVE LEADERSHIP & RESPONSIBILITY SPLIT
Praveen G. Menon — Founder & Managing Partner (IT Strategy, SaaS Architecture & B2B Content Systems)
Vishnudas Menon — Co-Founder & Director of Operations (Business Operations, Strategic Alliances & CX)
Phoenix Solutions · Executive Execution Blueprint
1 / 9

## Slide 2
EXECUTIVE ARCHITECTURE
6-Phase Execution Framework (2 Phases / Month)
MONTH 1 (Days 1–30)
FOUNDATION & LAUNCH
FIRST HALF OF MONTH:
• Phase 1 (Days 1–15): Digital Asset & Target List Setup
SECOND HALF OF MONTH:
• Phase 2 (Days 16–30): Warm Direct Outreach & First Content
MONTH 2 (Days 31–60)
PARTNERSHIPS & AUDITS
FIRST HALF OF MONTH:
• Phase 3 (Days 31–45): Alliance Outreach & Weekly Publishing
SECOND HALF OF MONTH:
• Phase 4 (Days 46–60): Discovery Calls & RFP Proposals
MONTH 3 (Days 61–90)
CONVERSION & RETAINERS
FIRST HALF OF MONTH:
• Phase 5 (Days 61–75): Closing First Clients & Delivery
SECOND HALF OF MONTH:
• Phase 6 (Days 76–90): Recurring Retainers & Testimonials
Phoenix Solutions · Executive Execution Blueprint
2 / 9

## Slide 3
MONTH 1 · DAYS 1 TO 15
Phase 1: Foundation & Digital Setup
PRAVEEN G. MENON — TECH & CONTENT
1. Digital Asset Audit: Verify live domain (phoenixsolutions.co), SSL security, contact form routing, and email endpoints (pgmenon@live.com).
2. Core Service Collateral: Finalize executive 1-pager PDFs detailing the 3 practice suites (IT Strategy, Business Dev, B2B Content).
3. LinkedIn Profile Alignment: Update headline and bio to reflect Founder & Managing Partner, Enterprise IT & Content Systems Advisory.
VISHNUDAS MENON — OPERATIONS & CX
1. Target Prospect Database: Compile a initial curated target list of 50 enterprise decision-makers (CTOs, Founders, Directors of BizDev).
2. CRM Lead Tracking Setup: Configure internal lead pipeline to track inbound queries, discovery call schedules, and deal stages.
3. LinkedIn Profile Alignment: Update headline and bio to reflect Co-Founder & Director of Operations, Client Engagement & BizDev.
Phoenix Solutions · Executive Execution Blueprint
3 / 9

## Slide 4
MONTH 1 · DAYS 16 TO 30
Phase 2: Warm Direct Outreach & Initial Positioning
PRAVEEN G. MENON — TECH & CONTENT
1. First Thought Leadership Launch: Publish 2 high-impact technical articles/carousels on LinkedIn covering Modular Cloud ERP Schemas.
2. Warm Network Introduction: Send direct personalized executive briefs to 20 warm senior tech contacts in Praveen’s network.
3. Initial Discovery Calls: Conduct 20-minute technical discovery calls with incoming warm inquiries to identify system friction.
VISHNUDAS MENON — OPERATIONS & CX
1. Warm Outreach Campaign: Reach out directly to 25 warm business contacts in Vishnu’s network via phone/message to introduce Phoenix Solutions.
2. 48-Hour Follow-Up Cadence: Execute structured follow-up calls with all Phase 1 prospects to lock in discovery calls.
3. Discovery Call Scheduling: Manage pre-call discovery questionnaires and send executive calendar invites for booked sessions.
Phoenix Solutions · Executive Execution Blueprint
4 / 9

## Slide 5
MONTH 2 · DAYS 31 TO 45
Phase 3: Partnership Engines & Weekly Publishing
PRAVEEN G. MENON — TECH & CONTENT
1. Weekly LinkedIn Cadence: Publish 1 technical breakdown per week covering AI Workflow Automation and Generative Engine Optimization (GEO).
2. Diagnostic Audit Templates: Finalize standardized technical audit checklists for IT strategy and custom SaaS database reviews.
3. Joint Proposal Frameworks: Draft flexible proposal templates for co-selling partners and strategic joint ventures.
VISHNUDAS MENON — OPERATIONS & CX
1. Alliance Partner Outreach: Initiate discussions with 15 non-competing technology providers and advisory firms for co-selling alliances.
2. Target Account Outreach: Begin targeted professional outreach to 15 new cold accounts from the primary target list.
3. SLA & Response Governance: Monitor lead response times, ensuring all incoming inquiries receive an executive response within 12 hours.
Phoenix Solutions · Executive Execution Blueprint
5 / 9

## Slide 6
MONTH 2 · DAYS 46 TO 60
Phase 4: Discovery Audits & Client Pitching
PRAVEEN G. MENON — TECH & CONTENT
1. Lead Technical Discovery: Conduct in-depth technical audit calls for qualified prospects, mapping legacy bottlenecks.
2. Deliver Roadmap Findings: Present custom IT strategy and modular ERP architecture roadmap presentations to prospective clients.
3. RFP & Proposal Engineering: Tailor comprehensive commercial proposals detailing implementation scope, timelines, and deliverables.
VISHNUDAS MENON — OPERATIONS & CX
1. Commercial Discovery Calls: Lead commercial and business operations discovery discussions alongside Praveen.
2. Proposal Follow-Up & Negotiation: Deliver commercial proposals, address operational questions, and finalize deal terms.
3. Co-Selling Charters: Formalize initial co-selling alliance charters with responsive technology and channel partners.
Phoenix Solutions · Executive Execution Blueprint
6 / 9

## Slide 7
MONTH 3 · DAYS 61 TO 75
Phase 5: Commercial Conversions & Project Onboarding
PRAVEEN G. MENON — TECH & CONTENT
1. Project Kick-Off Execution: Initiate Stage 1 Discovery Audits or Stage 2 SaaS/ERP builds for newly signed client accounts.
2. Database & API Build: Begin database schema design, workflow automation setup, or content mapping per contract scope.
3. Weekly Technical Reporting: Provide clear, structured weekly technical progress updates to active client stakeholders.
VISHNUDAS MENON — OPERATIONS & CX
1. Contracting & Invoicing: Execute formal client consulting agreements, issue deposit invoices, and manage payment terms.
2. Client Onboarding: Lead smooth client onboarding sessions, establishing communication channels and delivery expectations.
3. CX Quality Governance: Conduct bi-weekly check-in calls with active clients to ensure 100% operational satisfaction.
Phoenix Solutions · Executive Execution Blueprint
7 / 9

## Slide 8
MONTH 3 · DAYS 76 TO 90
Phase 6: Retainer Conversion & Systemized Scale
PRAVEEN G. MENON — TECH & CONTENT
1. Project Cutover & Delivery: Complete initial implementation engagements and present final executive outcome reports.
2. Retainer Proposals: Present monthly advisory retainer options to completed project clients for ongoing optimization.
3. Real-World Case Study: Author and publish 1 detailed client transformation case study based on completed Month 2/3 work.
VISHNUDAS MENON — OPERATIONS & CX
1. Recurring Retainer Closing: Finalize ongoing monthly advisory retainers with satisfied project clients.
2. Testimonials & Referrals: Request written executive testimonials from clients and secure 2 warm peer referrals.
3. 90-Day Performance Review: Review 90-day revenue targets, refine prospect database, and set Month 4–6 growth targets.
Phoenix Solutions · Executive Execution Blueprint
8 / 9

## Slide 9
ACCOUNTABILITY & TARGETS
90-Day Executive Key Performance Indicators (KPIs)
Key Performance Metric | Praveen (Tech & Content) | Vishnu (Operations & CX) | Combined 90-Day Target
LinkedIn Authority Touchpoints | 8 Technical Posts / Articles | 4 Profile / Update Posts | 12 Authority Touchpoints
Direct Outreach Connections | 20 Warm Tech Intros | 50 Direct Prospect Contacts | 70 Direct Connections
Qualified Discovery Audits | 6 Technical Audits | 6 Commercial Audits | 6 Booked Audits
Strategic Alliances Formed | 2 Co-Selling Technical Frameworks | 3 Alliance Charters Executed | 3 Active Partnerships
Closed Client Accounts | 2 IT Strategy / SaaS Builds | 1 GTM / Advisory Retainer | 2 – 3 Closed Client Contracts
Phoenix Solutions · Executive Execution Blueprint
9 / 9